## Tracker
XYZ MUSIC LOG |  |  | TC Framerate | 29.970 | drop |  | 13m 14s | of total music | 👈 do not edit gray cells |  |  |  | Errors? Unhide columns to right to reveal ☝ | Hide columns from here to right (don't edit these either) |  | 793.6595
| Cue # | Title | Video Source | Start | End | ⤨ | Duration | Status | Delivered Version | Notes | Use | Orig # | Orig Start | Err: Start | Err: End | Dur (secs) | Err: Orig Start
| 1m01 | Main Title | R1_2021-05-10 | 1000314 | 1014602 |  | 1m 43s | Ready for Orchestration | XYZ_1m01_v02c1_R1_2021-05-10_01000114 |  | MT | 1m01 | 1000314 |  |  | 102.6359
| 2m07 | Yaks Enter Spaceship | R2_2021-05-13 | 2124700 | 2164923 |  | 4m 03s | Revisions Needed | XYZ_2m07_v01c0_R2_2021-05-13_02124500 | Need to hire virtuoso kazoo player | BI | 2m08 | 2180002 |  |  | 242.7425
| 2m08 | The Great Shave | R2_2021-05-13 | 2164923 | 2190500 |  | 2m 15s | Writing In Progress |  |  | BI | 3m09 | 3000421 |  |  | 135.1684
| 3m12 | End Credits | R3_2021-05-17 | 3135808 | 3191114 |  | 5m 13s | Not Started |  |  | ET | 4m13 | 4092206 |  |  | 313.1128
IMPORTANT: set the correct TC Framerate for your project at the top of this sheet See Help tab at bottom for more (now delete this row)
(add rows above this)

## Project
YOUR MUSIC CO.
Production Code | XYZ
Program Title | Xylophones for Yaks at the Zoo
Episode Title
Episode #
Music | Your Name | Composer
Team | Grass Hopper | Assistant
| ... | ...
Production Co. | XYZ Productions
Client | Alfred Hitchcock | Director
Contacts | Linda Moneybags | Producer
| Ed Scissorhands | Video Editor
| ... | ...
External | Maurice Ravel | Orchestrator
Music | Decca T'halls | Recording Engineer
Contacts | ... | ...
👇 Add all composers and publishers, then just select their names in the Cue Sheet (PRO will fill in)
WRITERS | First (and Middle) | Last | PRO Affiliation | Lookup Key | PRO
| Your Full | Name | ASCAP | Your Full Name | ASCAP
| Grass | Hopper | BMI | Grass Hopper | BMI
(add rows above this)
PUBLISHERS | Name |  | PRO Affiliation
| Your Own Music, LLC |  | ASCAP
| XYZ Productions Music |  | BMI
(add rows above this)

## Schedule
Start Date | 2021-08-16
Deadline | 2021-10-28
☝ Tip: set when writing must wrap (with buffer for final orch., recording, etc.)
# Days Left | 6
see Progress tab for remaining work
👇 List specific work days (or delete them to count all days before deadline)
| Working Days | Notes
2021-08-16
2021-08-17
2021-08-18
| 2021-08-19 | Grass Hopper on vacation
| 2021-08-20 | Grass Hopper on vacation
2021-08-23
...
2021-10-22
| 2021-10-23 | pre-planned working Saturday
2021-10-25
2021-10-26
2021-10-27
2021-10-28
(add rows above this)

## Progress
do not edit this tab | In each Status |  |  | Cumulative (in or past Status) |  |  | == 6 DAYS LEFT == |  | Hide columns from here to right (don't edit these either)
Status | # Cues | Duration | % of Music | # Cues | Duration | % of Music | Remaining | Avg / Day | Duration (secs) | Cumulative Duration (secs) | Remaining (secs)
Not Started | 1 | 5m 13s | 39.45% | 4 | 13m 14s | 100% | 00s | 00s | 313.1128 | 793.6595 | 0
Writing In Progress | 1 | 2m 15s | 17.03% | 3 | 8m 01s | 60.55% | 5m 13s | 52s | 135.1684 | 480.5467 | 313.1128
Awaiting Notes | 0 | 00s | 0% | 2 | 5m 45s | 43.52% | 7m 28s | 1m 15s | 0 | 345.3784 | 448.2812
Revisions Needed | 1 | 4m 03s | 30.59% | 2 | 5m 45s | 43.52% | 7m 28s | 1m 15s | 242.7425 | 345.3784 | 448.2812
Conforms Needed | 0 | 00s | 0% | 1 | 1m 43s | 12.93% | 11m 31s | 1m 55s | 0 | 102.6359 | 691.0237
Ready for Orchestration | 1 | 1m 43s | 12.93% | 1 | 1m 43s | 12.93% | 11m 31s | 1m 55s | 102.6359 | 102.6359 | 691.0237
Session Prep Needed | 0 | 00s | 0% | 0 | 00s | 0% | 13m 14s | 2m 12s | 0 | 0 | 793.6595
Ready for Recording | 0 | 00s | 0% | 0 | 00s | 0% | 13m 14s | 2m 12s | 0 | 0 | 793.6595
Ready for Mixing | 0 | 00s | 0% | 0 | 00s | 0% | 13m 14s | 2m 12s | 0 | 0 | 793.6595
DONE | 0 | 00s | 0% | 0 | 00s | 0% | 13m 14s | 2m 12s | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595
[9 empty] | 0 | 0 | 793.6595

## Cue Sheet
Xylophones for Yaks at the Zoo
Music Cue Sheet
|  | Cue Sheet Classification: | Original | [7 empty] | Program (series, film, etc.) Title: | Xylophones for Yaks at the Zoo
|  | Date Prepared: | [8 empty] | Program Title AKA(s):
Episode Title:
Episode Title AKA(s):
|  | Initial Airdate: | [8 empty] | Episode Number:
|  | Category: | [8 empty] | Production Number: | XYZ
Version:
|  | Network/Source: | [8 empty] | Production Company: | XYZ Productions
Mailing Address:
|  | Program/Show Duration: | 0 | min. | 0 | sec. |  |  |  |  | Cue Sheet Prepared By:
|  | Total Music Duration: | 13 | min. | 14 | sec. | (auto calc.) |  |  |  | Email Address:
S_pesD3-6-2
Usage Codes: BI = Background Instrumental ¦ BV = Background Vocal ¦ VI = Visual Instrumental ¦ VV = Visual Vocal ¦ MT = Main Title Theme ¦ ET = End Title Theme ¦ Logo
👇 Prod. Co. must convert 👇
| Cue Title |  | TC In |  |  | TC Out |  | Duration |  |  | Composer/Writer | Composer/Writer | Publisher | (optional) | PRO | %
Seq. # | (Song/Track Name) | Usage | HH:MM:SS:FF |  |  | HH:MM:SS:FF |  | min. | sec. | Role | First (and Middle) Name | Last Name | Name | IPI # | Affiliation | Shares
1 | Main Title | MT | 1000314 |  |  | 1014602 |  | 1 | 43 | Composer | Your Full | Name |  |  | ASCAP | 100%
[10 empty] | Publisher |  |  | XYZ Productions Music |  | BMI | 100%
2 | Yaks Enter Spaceship | BI | 2124700 |  |  | 2164923 |  | 4 | 3
3 | The Great Shave | BI | 2164923 |  |  | 2190500 |  | 2 | 15
4 | End Credits | ET | 3135808 |  |  | 3191114 |  | 5 | 13

## Config
👇 Advanced settings
| Setting | Value | (Hidden)
| # Cue Sheet Rows / Cue | 4 | 168
👇 Customize your available statuses
| Status | Color
| Not Started | blank
| Writing In Progress | yellow
| Awaiting Notes | blue
| Revisions Needed | red
| Conforms Needed | red
| Ready for Orchestration | blue
| Session Prep Needed | red
| Ready for Recording | blue
| Ready for Mixing | blue
| DONE | green
(add rows above this)

## Help
What's this for? | For film & TV composers, spreadsheet to track progress of music cues with custom timecode features. Designed to be a collaborative document for use throughout a project, with the Cue Sheet tab used at the end to hand off to your production company (who submits it to PROs).
Help videos | TODO: Link to YouTube videos going over
How to use | Do NOT edit any gray cells (they contain formulas that automatically fill in the values). Configure first: timecode framerate (in Tracker tab) and the # of rows you need per cue in the Cue Sheet (in Config tab). Feel free to customize statuses + colors as well. Fill in basic project information, including writers and publishers with their PRO affiliations (Project tab). Set a project deadline and optionally list all working days (Schedule tab). Adding more rows: right click a row number above "(add rows above this)" and then insert new rows. Note that FORMULAS ARE NOT AUTOMATICALLY COPIED into new rows, so for the Tracker tab, you'll need to copy these down manually, including for the hidden columns off to the right (or paste an existing row into the newly inserted one).
Cue Sheet handoff: When finished, I recommend starting with a fresh copy of the RapidCue Blank Cue Sheet Template (see linke below) and copying values (without formatting) over in sections. This can be a little finicky, so watch the Music Log In Depth help video above for tips. Note that the Cue Sheet tab differs from the RapidCue template in listing Timecode In and Timecode Out (which should be from your scored reel versions), and the production company is responsible for filling in final Time In and Time Out h, mm, and ss values in the final long-play (i.e. all reels together in one big file) program. Or they may only submit durations (since that's what affects royalty payouts). Confirm with your production company, and verify the final cue sheet and timings when possible!
RapidCue Blank Cue Sheet Template
See the code | excel-timecode on GitHub

## hidat (hidden)
pesD3-6-6 | YesNo | Classification | Version | Usage | Role | Category | Affiliation
7/22/2016, 6:41 PM | Yes | Original | (Unknown) | BI |  | Arts
| No | Revision | Airline | BV | Composer | Broadcast | ASCAP
|  |  | Cable | VI | Publisher | Broadcast Series | BMI
|  |  | Edited for TV | VV |  | Cartoon | SESAC
|  |  | Home Video | MT | Arranger | Cartoon Series
|  |  | Internet | ET |  | Children's Show | SOCAN
|  |  | Music Video | Logo |  | Children's Special | PRS
|  |  | Network |  |  | Cinema | NS
|  |  | New Media |  |  | Daytime Soap | PD
|  |  | Non Broadcast |  |  | Entertainment News | Unknown
|  |  | Non US |  |  | Finance
|  |  | PBS |  |  | First Run Syndicated | ABRAMUS
|  |  | Syndicated |  |  | Game Show | ACAM
|  |  | Theatrical |  |  | Health | ACDAM
|  |  | Theme Park |  |  | Hobbies/Craft | ACUM
|  |  | US |  |  | Instructional | ADAGP
[6 empty] | Magazine News | ADDAF
[6 empty] | Mini-Series | AEPI
[6 empty] | Movie | AGADU
[6 empty] | Music | AGAYC
[6 empty] | Music Special | AKKA
[6 empty] | Music Video | AKM
[6 empty] | Music Video Series | ALBAUTOR
[6 empty] | News | ALCS
[6 empty] | Non Broadcast | AMAR
[6 empty] | Non Broadcast Series | AMCOS
[6 empty] | Novela | AMRA
[6 empty] | Paid Programs | APA
[6 empty] | Pelicula | APDASPAC
[6 empty] | Play-off Sport | APDAYC
[6 empty] | Pseudo-Sport | APRA
[6 empty] | Public Affairs | ARGENTOR
[6 empty] | Reality | ARS
[6 empty] | Religious | ARTISJUS
[6 empty] | Religious Special | ASCAP
[6 empty] | Seasonal Special | ASSIM
[6 empty] | Series | AUME
[6 empty] | Special | AWA
[6 empty] | Sporting Event | BBDA
[6 empty] | Sports | BCDA
[6 empty] | Sports Anthology | BEELDRECH
[6 empty] | Sports Related | BGDA
[6 empty] | Syndicated | BILD-KUN
[6 empty] | Talk Show | BMDA
[6 empty] | Team vs. Team Sport | BMI
[6 empty] | Theme Park | BNDA
[6 empty] | Theme Park Series | BONO
[6 empty] | Trailer | BSCAP
[6 empty] | TV Movie | BSDA
BUBEDRA
BUCUDA
BUMA
BUMDA
BURIDA
BUS
BUTODRA
CAPAC
CASH
CASP
CHA
CMRRA
COMPASS
COPY-DAN
COSCAP
COSGA
COSOMA
COTT
DACS
DALRO
DPRS
DSS
EAU
ECCO
FILMAUTOR
FILSCAP
FOX
GEMA
GESATCH
GMR
HAA
HDS
HUNGART
IMRO
IPRS
JACAP
JASRAC
KCI
KODA
KOMCA
KOPIOSTO
LAA
LATGA
MACP
MASA
MCPS
MCSC
MCSK
MCSN
MCT
MESAM
MRS
MSG
MUSICAUT
MUST
NASCAM
NCB
NS
OMDA
ONDA
OSA
PD
PROCAN
PRS
RAO
SABAM
SACD
SACEM
SACERAU
SACM
SACVEN
SADA
SADAIC
SADEMBRA
SADH
SAMRO
SARRAL
SAYCE
SAYCO
SAZAS
SBACEM
SBAT
SCAU
SCD
SDRM
SESAC
SGAE
SIAE
SICAM
SLPRS
SOBODAYC
SOCAN
SOCINADA
SOCINPRO
SODACT
SODART
SODRAC
SOFAM
SOKOJ
SOMAAP
SONECA
SOZA
SPA
SPAC
SPACEM
SPACEMF
STEF
STEMRA
STIM
SUISA
TEATERAU
TEOSTO
TONO
UACRR
UBC
UCMR
Unknown
VAGA
VBK
VCPMC
VEGAP
VISCOPY
WORT
ZAIKS
ZAMCOPS
ZAMP
ZIMRA